## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
AS A Developer I WANT to submit a request to create a Need class so THAT I can implement the cupboard. | 1. GIVEN I submit a request for the inventory WHEN products exist in the inventory THEN the system should return a list of products and a status code of 200 (OK) 2. GIVEN I submit a request for the inventory WHEN no products exist in the inventory THEN the system should return an empty list of products and a status code of 200 (OK) | Pass | AG | Pass | JMS 11/13
AS a Developer I WANT to submit a request to get the the needs in the cupboard whose name contains the given text, SO THAT I have access to only that subset of needs. | Allows two types of logs: Helper and Manager. This forwards user into a different page based on their clearance.Fails if wrong password is used to log in. | Pass | AG | Pass | JMS 11/13
AS a User I WANT to be able to log out when I have done with my donation SO THAT my account is not used without my knowledge by someone else. | As a User, I have to ability to log out so that another user cannot use my account from the same | Pass | AG | Pass | JMS 11/13
As a new User, I WANT to register on the platform using my email and create a password, SO THAT I can start using the donation platform. | As a new User I can create a new user account to start donating. As a user I can make a unique login name and wont allow me to make a duplicate existing user account. When creating my account, it needs to make sure I correctly inputted types and does password match test. | Pass | AG | Pass | JMS 11/13
AS a Developer I WANT to be able to view the list of needs in the cupboard in a graphical way rather than just a list, so that I can easily go through the needs. | Reloads every time a specific action is done for example deleting a need. The cupboard is what is always displayed unless otherwise logged out of in checkout cart. | Pass | GE | Pass | JMS 11/13
AS a Developer I WANT to make a button when clicked will make a new need in the cupboard, and display the new cupboard. So that my program is user friendly | Checks if input types are correct, for instance won't accept string as amount of a specific need. | Pass | GE | Pass | JMS 11/13
AS a User I WANT I want to have a clear user-friendly layout SO THAT I can navigate the page with ease. | Given I login as a user, the home page is the first page shown and it should be easy to navigate | Pass | AO | Pass | JMS 11/13
As a User I want to see what I added to my cart, and it shows the checkout cart with the total cost | Given the I am a user with items in my cart, when I go to the checkout section there should be a schekout button. After a successful checkout it updates the amount in cupboard |  |  | Pass | JMS 11/13
As a user I want to be able to delete an item in my cart. | As a user when I delete the delete button in chekout, the need is removed from my cart |  |  | Pass | JMS 11/13
As a user I want to be able to navigate to the home page from other pages | On each page there needs to be a go home buttons |  |  | Pass | JMS 11/13
As a helper I want to be able to search for a need in the helper cupboard by typing the name in the search box | On the helper cupboard page there needs to be a search textbox that searches input need |  |  | Pass | AR 11/19
As an admin I want to be able to search for a need in the admin cupboard by typing the name in the search box | On the admin cupboard page there needs to be a search textbox that searches input need |  |  | Pass | AR 11/19
As a helper, I don’t want to see a need that has reached it's donation target in the helper cupboard | Given the donation target has been reached for a need, that need is no longer visible in helper cupboard |  |  | Pass | AR 11/19
As an admin, I want to be able to show an announcement in the home page for all the helpers to see | On the admin cupboard page, there needs to be a textbox that takes in a statement from the admin shows it in the helper cupboard page |  |  | Pass | AR 11/19
As an admin, I want to be able to delete an announcement, from the admin cupboard page | On the admin cupboard page, there needs to be a delete button that deletes selected announcement |  |  | Pass | AR 11/19
As an Helper I want to be see announement made by admin the the helper cupboard page | Given an announcement by admin, it should be displayed in the helper cupboard page |  |  | Pass | AR 11/19
As an Admin I want to be upload announcement from admin page to be shown in helper cupboard page | Uploaded announcements should be prominently displayed on the helper cupboard page. |  |  | Pass | AR 11/19
AS a User I WANT I want to see an announcement on the front page SO THAT I can be up to date with the MOROCCO fund page. | The announcement should be prominently displayed on the front page of the website. |  |  | Pass | AR 11/19
AS a Developer I WANT to submit a request to delete a need from the cupboard by selecting a specific need and touching the delete action button, FOR EASY navigation of program. Cupboard will display new needs. | The need should be deleted and returned to cupboard view |  |  | Pass | AR 11/19